## Projects
Project status as at 31 December 2016
| Project Status | Metric | NSW | Vic | Qld | WA | SA | Tas | NT | ACT | Aust
2016 | Completed | Project Numbers | 46 | 26 | 46 | 15 | 10 | 17 | 14 | 2 | 0
2016 | Underway | Project Numbers | 25 | 19 | 36 | 7 | 8 | 10 | 6 | 1 | 2
2016 | Pending | Project Numbers | 43 | 43 | 63 | 15 | 7 | 20 | 10 | 2 | 0
2016 | Total | Project Numbers | 114 | 88 | 145 | 37 | 25 | 47 | 30 | 5 | 2
2016 | Completed | Total Project Cost | 7328803651 | 5066590442 | 5943008035 | 1669928869 | 124193551 | 319205084 | 266868695 | 307531506 | 0
2016 | Underway | Total Project Cost | 29352413293 | 4163320000 | 5838590000 | 1126053661 | 2500410000 | 281620442 | 259789000 | 686000 | 365000000
2016 | Pending | Total Project Cost | 2684865000 | 1058500000 | 4260299000 | 7109710000 | 127400000 | 184350548 | 363752500 | 6000000 | 0
2016 | Total | Total Project Cost | 39366081944 | 10288410442 | 16041897035 | 9905692530 | 2752003551 | 785176074 | 890410195 | 314217506 | 365000000

## Milestones
Figure 32. National Partnership Agreement on Land Transport Infrastructure Projects
State | Key Project | Milestones | Status
NSW | WestConnex | M4 Widening: Construction 81 per cent complete. M4 East: Tunnelling commenced July 2016. King Georges Road: Opened to traffic December 2016. New M5: Tunnelling commenced November 2016. Australian Government concessional loan agreement finalised in November 2015. | In progress
NSW | Pacific Highway | Priority 1 package projects: All work completed in December 2015. 70 per cent of final highway length now complete. | In progress
VIC | M80 | The contract for the Sunshine Avenue to the Calder Freeway section was awarded in August 2016 and construction commenced in October 2016. | In progress
VIC | Western Highway - Ballarat to Stawell Duplication | Construction from Ballarat to Buangor was competed in April 2016. Construction from Buangor to Ararat is expected to commence in early 2017 and be completed in mid 2019. | In progress
VIC | Tullamarine Freeway Widening | The contract for the project was awarded in February 2016 and construction commenced in May 2016. | In progress
QLD | Gateway Upgrade North | Major construction commenced in February 2016 and is expected to be completed late 2018, weather permitting. A major traffic switch on Sandgate Road Bridge and Bicentennial Road interchange occurred December 2016. Construction on the Nundah Creek Bridge and the Sandgate Road Bridge is expected to be completed early 2017. | In progress
QLD | Bruce Highway | Cooroy to Curra – Section C: Construction commenced in March 2016 Boundary Road Upgrade: Construction commenced in May 2016. Tinana Interchange Upgrade: Construction commenced in July 2016. Cairns Southern Access – Stage 2: Construction commenced in June 2016. Townsville Northern Access Intersections Upgrade: Early works package commenced in July 2016. Arnot Creek Bridge Upgrade: Construction commenced in May 2016. Contracts have been awarded for Caloundra to Sunshine Motorway (September 16), planning studies for the Pine River to Caloundra section (July 16) and Cooroy to Curra – Section D detailed design phase (May 16) | In progress
QLD | Toowoomba Second Range Crossing | Major construction commenced in April 2016 and is expected to be completed late 2018, weather permitting. Works on the Viaduct started in September 2016 and construction on the Mort St Interchange commenced in November 2016. | In progress
WA | Perth Freight Link | Section Three (Tonkin Highway pinchpoint) is expected to be completed in early 2017. Contract was awarded for Section One (Roe 8) in October 2016, early works commenced in December 2016. On 15 January 2017, the WA Premier announced that the WA Government will proceed with the tunnel option for Section Two (in place of the previously announced surface upgrade of Stock Road and the Leach Highway). This follows the Australian Government’s announcement in April 2016 of an additional $260.8 million to allow the tunnel option to proceed. | In progress
WA | NorthLink WA | Swan Valley Bypass project: Contract was awarded for Stage One in December 2016 and a contract for Stage Two is expected to be awarded in January 2017. Construction of both stages is expected to commence in mid-2017. Tonkin Grade Separations: Contract awarded in January 2016, construction commenced in June 2016. | In progress
SA | North-South Corridor | Darlington Upgrade: Construction commenced in September 2016. Northern Connector: Construction commenced in December 2016. Torrens Road to River Torrens: Construction commenced in August 2015, and construction has begun on the Outer Harbour rail overpass. | In progress
TAS | Midland Highway | Seven of the 18 projects approved for construction have been completed with a further four scheduled for completion in 2017. Construction is expected to commence in 2017 on an additional four projects which are currently in planning. Further projects are being developed by Tasmania for delivery over the next seven years. | In progress
ACT | Majura Parkway | Construction on the project was completed and the new parkway opened to traffic in April 2016. | Complete
NT | Northern Territory Roads Productivity Package | The package consists of six projects across the Northern Territory. Three of the six projects approved for construction have been completed since December 2014. Construction is continuing on the remaining three projects. | In progress
NT | Northern Territory Roads Package | Road Safety and Fatigue Management Initiatives; Construction commenced in July 2016. Strengthening and Widening works: Construction commenced in January 2015 and is due for completion mid-2018. Flood Immunity Improvements: Construction was completed in November 2016. | In progress

## Description
Measure | Deliver major land transport infrastructure projects on schedule
Short title | Road and rail projects
Status | On track
Updated | 2016
Desc Body | The following progress has been made on the NPALTIP:
Nationally, as at December 2016, 176 road and rail projects have been completed, 114 projects are underway (including cross jurisdictional projects), and 203 are pending (in planning or not yet started). The completed projects are designed to provide for improved safety, connectivity and reduced travel times.
The NPALTIP Schedules are being revised to include election commitments and changes following the 2016-17 budget process.
Notes | The key project status is at January 2017 reflecting the Department of Infrastructure and Regional Development's latest available information.
Only includes Investment Programme, Building Australia Fund, Managed Motorways, National Highway Upgrade Programme, Infrastructure Growth Package, Northern Australia Roads and Beef Road Programme, and 2016 Federal Election Commitments projects. Total investment includes outstanding projects funded under previous governments.
Completed projects have achieved their main purpose, e.g. the road works are opened to traffic. Projects underway are either currently under construction or, in the case of study projects, have commenced. Pending projects are those currently in the planning stage or that have not yet reached their scheduled construction start date.
All projects have been counted in the Project Numbers, however, not all funding amounts are available as yet.