## Data
NPARIH capital works progress, number of new houses and refurbishments, by state and territory, 2008-2016
|  | NSW | Qld | WA | SA | Tas | NT | Aust
2016 | New houses | 263 | 836 | 708 | 239 | 12 | 1214 | 3272
2016 | Refurbishments | 1009 | 1490 | 1561 | 304 | 57 | 2929 | 7350
`

## Description
Measure | 4,200 new houses to be delivered by 2018; 4,800 refurbishments to be delivered by 2014.
short title | Construction and refurbishment of homes
Status | On track
Updated | 2016
Desc Body | From 2008 to the end of October 2015, the NPRH and NPARIH delivered a total of 3,272 new houses against the 2018 COAG target of 4,200.
A total of 7,350 refurbishments were delivered, considerably exceeding the 2018 COAG target of 4800.
Notes | Victoria is not included in these analyses as no Commonwealth funding was provided to Victoria under the NPARIH for the construction of new houses or refurbishment of existing stock.
Victoria and Tasmania exited the NPARIH in 2014 and are not part of the Remote Housing Strategy.
New South Wales exited the NPARIH in 2015 and is not part of the Remote Housing Strategy
ACT | The ACT does not participate in this National Partnership Agreement.
Vic | Victoria does not participate in this National Partnership Agreement.