## Data
NPARIH capital works progress, number of new houses and refurbishments, by state and territory, 2008-2015
|  | NSW | Qld | WA | SA | Tas | NT | Aust
2015 | New | 241 | 653 | 622 | 235 | 12 | 1149 | 2912
| Refurbishments | 1003 | 1490 | 1440 | 286 | 57 | 2929 | 7205
`

## Description
Status | On track
Updated | 2015
Desc Body | Since the commencement of NPARIH to the end of October 2015, a total of 2,957 new houses have been delivered against the COAG new house target.
A total of 7,206 refurbishments have been delivered, considerably exceeding the COAG refurbishment target.
Other Benchmarks | Under NPARIH, states and the Northern Territory have a 20 per cent Indigenous employment target for capital works. Over the life of NPARIH, all jurisdictions have met or exceeded this target. In addition, the Northern Territory Government has consistently delivered against a 40 per cent Indigenous employment target for property management and a 40 per cent Indigenous employment target for tenancy management, as outlined in the Northern Territory’s 2014- 16 Implementation Plan to the NPARIH.
Queensland has consistently exceeded the 20 per cent Indigenous employment target for capital works, with over 85 per cent of all available jobs in construction, repairs and maintenance during 2014-15 undertaken by Aboriginal and Torres Strait Islander workers.
Notes | NPARIH notional targets extend to 2014 for refurbishments and to 2018 for new build houses.
Victoria is not included in these analyses as no Commonwealth funding was provided to Victoria under the NPARIH for the construction of new houses or refurbishment of existing stock.
Victoria and Tasmania are not currently a part of NPARIH as they exited in 2014.