## Data
NPARIH capital works progress, number of new houses and refurbishments, by state and territory, 2008-2016
|  | NSW | Qld | WA | SA | Tas | NT | Aust
2016 | New houses | 263 | 833 | 708 | 239 | 12 | 1214 | 3269
2016 | Refurbishments | 1009 | 1490 | 1561 | 304 | 57 | 2929 | 7350
`

## Description
Measure | 4,200 new houses to be delivered by 2018; 4,800 refurbishments to be delivered by 2014.
short title | Construction and refurbishment of homes
Status | On track
Updated | 2016
Desc Body | From 2008 to the end of October 2016, the NPRH and NPARIH delivered a total of 3,269 new houses against the 2018 COAG target of 4,200.
A total of 7,350 refurbishments were delivered, considerably exceeding the 2018 COAG target of 4800.
Notes | NPARIH notional targets extend to 2014 for refurbishments and to 2018 for new build houses.
Victoria and Tasmania exited the NPARIH in 2014 and are not part of the NPRH.
New South Wales exited the NPARIH in 2015 and is not part of the NPRH.
Totals include dwellings built from Commonwealth Own Purpose Expense funding under NPARIH.
ACT | The ACT does not participate in this National Partnership Agreement.
Vic | Victoria does not participate in this National Partnership Agreement.
Source | NATSISS 2008 and 2014/15
State and Territory governments