## Data1
Road and Rail Projects as of November 2015 - Progress of projects, by number
|  | NSW | Vic | Qld | WA | SA | Tas | ACT | NT
2015
| Completed | 33 | 16 | 33 | 10 | 10 | 12 | 0 | 9
| Underway | 32 | 15 | 29 | 8 | 4 | 8 | 1 | 7
| Pending | 14 | 17 | 38 | 8 | 6 | 8 | 2 | 6

## Data2
Road and Rail Projects as of November 2015 - Progress of projects, by proportion of funds
|  | NSW | Vic | Qld | WA | SA | Tas | ACT | NT
2015
| Completed | 13.7909 | 69.4321 | 33.6637 | 5.839 | 7.0927 | 42.8085 | 0 | 36.2031
| Underway | 73.92 | 26.2416 | 36.3747 | 21.8383 | 83.9404 | 25.8258 | 98.5036 | 35.9565
| Pending | 12.2891 | 4.3263 | 29.9616 | 72.3227 | 8.9669 | 31.3657 | 1.4964 | 27.8404

## Data3
Figure 32. National Partnership Agreement on Land Transport Infrastructure Projects
State | Key Project | Milestones | Status
NSW | WestConnex | M4 Widening: Early works commenced on 8 March 2015. King Georges Road: Early work commenced in July 2015. New M5: Preferred contractor announced in August 2015. Contract awarded in November 2015. Australian Government concessional loan agreement finalised in November 2015. | In progress
NSW | Pacific Highway | Woolgoolga to Ballina project: Contract awarded in June 2015. Priority 1 package projects: All work completed in December 2015. | In progress
VIC | M8o | VicRoads invited industry for expressions of interest for the design and construction of the next priority section from Sunshine Avenue to Calder Freeway in September 2015 which closed in October 2015. | In progress
VIC | Western Highway - Ballarat to Stanwell Duplication | The duplication from Ballarat to Beaufort is complete, with construction from Beaufort to Buangor underway and expected to be completed in early 2016. Construction from Buangor to Ararat is expected to commence in mid-2016 and be completed in mid-2018. | In progress
QLD | Bruce Highway | The first tranche of projects being undertaken as part of the Bruce Highway Safety Package, including Overtaking Lane and Pavement Widening programmes, commenced in early 2015. Australian Government funding for these programmes has been approved via the schedule of works through to 2018-19. | In progress
QLD | Toowoomba Second Range Crossing | Early pre-construction activities commenced in December 2015, including geotechnical drilling and the establishment of a project office on site in Toowoomba. | In progress
WA | Perth Freight Link | Roe Highway Extension (Section One): On hold, due to the Western Australia Supreme Court decision in December 2015 which overturned environmental approvals. Roe Highway pinch point widening (Section Three): Contract awarded - December 2015. | In progress
WA | NorthLink | Swan Valley Bypass project: Expressions of Interest for Stage One closed in November 2015. Tonkin Grade Separations: Funding and scope increase, to include an upgrade to three lanes in each direction, approved in December 2015; Contract awarded in January 2016. | In progress
SA | North-South Road Corridor | The Australian Government announced up to $788 million for the Northern Connector project in September 2015. The Minister for Major Projects provided in-principle agreement to further increase the scope of both the Torrens to Torrens project and the Darlington project within the existing budget allocation which was received in December 2015. | In progress
TAS | Midland Highway | Seven of the 14 projects approved for construction have been completed. Four projects will commence construction in early 2016, with an additional two commencing later in the year. Further projects are being developed by Tasmania for delivery over the next eight years. | In progress
ACT | Majura Parkway | The Fairbairn Avenue bridges and the northbound bridge over the Molonglo River opened in November 2015, allowing two-way traffic to traverse the entire length of the Majura Parkway. The project is expected to be complete by mid-2016. | In progress
NT | Northern Territory Roads Producitivity Package | Since December 2014, construction has commenced on three projects, with one completed. | In progress

## Description
Status | On track
Updated | 2015
Desc Body | The following progress has been made on the NPALTIP:
Nationally, as at November 2015, 123 road and rail projects have been completed, 106 projects are underway (including cross-jurisdictional projects), 99 are pending (in planning or not yet started) and 5 projects are not proceeding. The completed projects are designed to provide for improved safety, connectivity and reduced travel times.
The NPALTIP Schedules were revised to include projects following the 2015-16 Budget and have been signed by New South Wales, Victoria, Western Australia, Tasmania, Australian Capital Territory and the Northern Territory.
Notes | The key project milestone statuses are as at January 2016, reflecting the Department of Infrastructure and Regional Development’s latest available information. The remainder of this update uses November 2015 data, as the most recent complete quarter.
Only includes Investment and Off-Network Programme, Building Australia Fund, Managed Motorways, National Highway Upgrade Programme and Infrastructure Growth Package projects. Total investment includes outstanding projects funded under previous governments.
Completed projects have achieved their main purpose, e.g. the road works are opened to traffic. Projects underway are either currently under construction or, in the case of study projects, have commenced. Pending projects are those currently in the planning stage or that have not yet reached their scheduled construction start date.